## Gantt chart
Task | Start Date | End Date | Duration (Weeks)
Phase 1: Project Planning and Definition (Week 1-2)
- Literature review and analysis | 2023-12-15 | 2023-12-17 | 1
- Project scope definition | 2023-12-18 | 2023-12-22 | 1
- Stakeholder identification and engagement | 2023-12-19 | 2023-12-22 | 1
- Data needs assessment and acquisition plan | 2023-12-20 | 2023-12-24 | 1
Phase 2: Data Collection and Preparation (Week 3-4)
- Transit data collection (traffic patterns, vehicle speeds) | 2023-12-25 | 2024-01-05 | 2
- Ridership data acquisition (passenger volumes, travel patterns) | 2024-01-02 | 2024-01-12 | 2
- Data cleaning and pre-processing | 2024-01-03 | 2024-01-14 | 2
Phase 3: Model Development and Training (Week 5-6)
- Route optimization models (machine learning algorithms) | 2024-01-15 | 2024-01-26 | 2
- Demand forecasting models (statistical analysis) | 2024-01-17 | 2024-01-28 | 2
- User app development (real-time information, trip planning) | 2024-01-19 | 2024-01-31 | 2
Phase 4: Testing and Evaluation (Week 7)
- Model testing and validation with real-world data | 2024-02-01 | 2024-02-09 | 1
- User app beta testing and feedback collection | 2024-02-02 | 2024-02-10 | 1
Phase 5: Deployment and Monitoring (Week 8)
- System deployment and integration with existing infrastructure | 2024-02-12 | 2024-02-14 | 1
- Performance monitoring and feedback loop for continuous improvement | 2024-02-15 | 2024-02-23 | 1